## Operations
LAST UPDATE: [INSERT DATE]
ORGANIZATIONAL STRUCTURE
STRATEGY | TACTIC / ACTION | STRATEGIC PRIORITY | RESPONSIBLE PARTY | PERFORMANCE METRIC | PERFORMANCE TARGET | START DATE | END DATE (if applicable) | ESTIMATED FINANCIAL COST | STATUS | Strategic Priorities
Streamline Organizational Structure | Centralize common county-wide processes and systems under the County Administrator. | Effectiveness |  | Project Implemented | [5 empty] | Effectiveness | Implement operational efficiencies to reduce the costs and free up revenue
| Create county-wide organizational chart | Effectiveness |  | Project Implemented
| Create a finance, HR, and maintenance department | Effectiveness |  | Project Implemented
| Improve the county’s procurement process to be consistent county-wide. Maximize procurement rewards or benefits and identify joint procurement opportunities across departments or with other organizations. | Effectiveness |  | Project Implemented | [5 empty] | Growth | Work to increase the county's population and tax base in order to fund services
| Purchase a payroll program that is uniform for employees across all departments or enterprises | Effectiveness |  | Project Implemented | [5 empty] | Focus | Scale back or eliminate discretionary services that cannot provide sustainable revenue to cover their costs
Improve Financial Practices | Improve the county’s bond rating by targeting improvement opportunities identified in Moody’s Rating Action of February 2020 and Rating Change of March 2018 | Improvement |  | Maintain the existing Investment Grade rating for the county's general obligation debt, with improvement from A3 across a 5-year period | A2 Rating by 2025 |  |  |  |  | Improvement | Create a culture of continual improvement to sustain progress
| Create budget narratives summarizing how new initiatives or improvements implement the Strategic Plan | Improvement |  | Achieve and maintain a general fund balance equal to 25% of annual operating expenses | Set target for 2022, 2023, 2024
| Define value that could be added with 20% more funding, or lost due to a 20% reduction in funding | Improvement |  | Achieve and maintain a general fund balance equal to 25% of annual operating expenses | Set target for 2022, 2023, 2024
| Identify cuts that would not impact strategic planning goals or mandated services | Focus |  | Achieve and maintain a general fund balance equal to 25% of annual operating expenses | Set target for 2022, 2023, 2024
| Identify how departments would respond to unexpected cuts or events | Effectiveness |  | Achieve and maintain a general fund balance equal to 25% of annual operating expenses | Set target for 2022, 2023, 2024
| Develop a capital improvement plan inclusive of facilities, roads, and equipment | Effectiveness |  | Project Implemented
| Analyze the county’s indirect rate to capture highest possible amount of grant funding, and establish a metric for productivity and efficiency | Effectiveness |  | Increase non-tax revenue as a portion of overall revenue through grants and fees | Development of indirect rate by 2023. Maintain steady rate or lower annually
| Increase discretionary and variable revenue source (fines, fees, grants, etc.) as a portion of the overall budget | Effectiveness |  | Increase non-tax revenue as a portion of overall revenue through grants and fees | Develop baseline data, and set metrics for annual improvement
Increase Coordination | Engage in joint procurement materials and equipment whenever possible | Effectiveness |  | Develop list of materials for joint procurement
| Engage in joint contracting for capital projects to find savings resulting from reduced mobilization fees, increased competitive bidding, etc | Effectiveness |  | Develop list of projects for joint contracting
| Explore opportunities to share or contract staffing services | Focus
| Create additional and modern methods to communicate events and initiatives, and to generate direct input from the community. This could include community engagement via a new website or a social media presence | Growth |  | Development of new county website
| Coordinate community develop and land use decision-making in Richland Center among institutional partners such as Richland County, Richland Center, Richland Hospital, and Richland Local School District | Growth |  | Creation of a land use planning working group incorporating these organizations
WORKFORCE
STRATEGY | TACTIC / ACTION | STRATEGIC PRIORITY | RESPONSIBLE PARTY | PERFORMANCE METRIC | PERFORMANCE TARGET | START DATE | END DATE (if applicable) | ESTIMATED FINANCIAL COST | STATUS
Improve employee pay and HR policies | Obtaining market value for employee wages as determined through the county’s 2018 wage study | Improvement |  | Meet the 2018 salary schedule commitments for county staff. | Market Value wages met by 2025
| Monitor the compensation and classification system for all positions to ensure positions remain market-competitive | Improvement |  | Project Implemented | Market Value wages met by 2025
| Give annual pay raises | Improvement |  | Project Implemented | Annual Pay Raises built in budgets
| Develop a uniform performance evaluation process that includes annual reviews, 6-month check-ins, and exit interviews | Improvement |  | Develop baseline data on turnover, identify reasons for turnover, and reduce annual non-retirement and non-termination turnover | Set metric for annual turnover and targeted reduction if needed
| Develop a uniform set of human resources policies and procedures to improve transparency and accountability throughout the organization, including an update to the employee handbook and other related documents | Effectiveness |  | Project Implemented
Develop a culture of support for employees | Celebrate success and the professional and personal achievements of employees. Recognize new hires, retirements, and year-of-service milestones. Build a culture that supports and celebrates its people | Improvement |  | Develop parameters for this process, empower staff to lead
| Increase vacation time for new employees | Improvement |  | Increased vacation for new employees | 2022 - research practices, develop and implement vacation policy 2023 - vacation policy implemented
| Evaluate flexible work schedules | Improvement |  | Flexible work policy implemented | 2022-2023 - research practices, develop and implement flexible work policy 2024 - flexible work policy implemented
| Enable and empower departments to develop celebratory or team-building events. Day-long departmental retreats or other benefits can help build culture at a minimal expense | Improvement |  | Develop parameters for departmental budgets. Submit with 2022 budget
| Create a total benefits program for employees that highlights total compensation and investment of the county in its employees, inclusive of salary, fringe benefits, wellness, and professional development | Improvement |  | Project Implemented | Procedures set up in 2022. Draft in 2023. Implemented by 2024
Prioritize service of staffing | For each unmet existing service or new service being proposed, evaluate staffing needs using the following analysis | Focus |  | Develop process.
CAPACITY
STRATEGY | TACTIC / ACTION | STRATEGIC PRIORITY | RESPONSIBLE PARTY | PERFORMANCE METRIC | PERFORMANCE TARGET | START DATE | END DATE (if applicable) | ESTIMATED FINANCIAL COST | STATUS
Invest in education of County Board Supervisors | Creation of a mentor program partnering tenured Supervisors with new Supervisors | Improvement |  | Process Implemented
| Hold informal meetings with outgoing Supervisors and their successors to facilitate knowledge transfer | Improvement |  | Process Implemented
| Fund new Supervisors’ attendance at annual Wisconsin Counties Association training or conferences | Improvement |  | Process Implemented
| Create an on-boarding folder summarizing expectations for supervisors |  |  | Project implemented
| Support the attendance by new Supervisors at major Committee meetings, such as attending Finance Committee meetings during the annual budget development process. Create a mechanism to share agendas with all County Board Supervisors in order to facilitate this | Improvement |  | Process explained and supervisors invited and empowered
| Support cross-training, collaboration, and peer learning between County Board Supervisors and their counter parts on the boards of outside partners, such as peer county boards, Neighborhood Services of Southwest Wisconsin, Southwest Wisconsin Community Action Program, Southwestern Wisconsin Regional Planning Commission, and the Southwest Wisconsin Workforce Development Board | Improvement |  | Process explained and supervisors invited and empowered
| Conduct annual on-going training covering basic concepts of local government, such as the role of counties, county government finances, the role of county boards, elections, and departmental work | Improvement |  | Process implemented | 2022 - establish training schedule 2023 - Begin implementing training
Deepen staff training in leadership and management | Sponsor department head training targeted at leadership and management, including Lean process training or UW Continuing Education certifications in Public Management or Human Resources | Improvement |  | Process implemented | 2022 - Identify department heads looking for training, build into 2023 budget
| Educate employees on how government works and the need for teamwork and partnership within county departments | Improvement
| Create a culture of sharing information and learning from peer counties | Improvement
| Ensure conference attendance and professional development is aligned with the goals of the Strategic Plan | Improvement |  | Process implemented | 2022 - Build this review into annual performacne evaluations, updating evaluation forms as needed and establishing procedures for evaluations if they don't exist.
| On-going training or education targeted at the evaluation, adoption, and implementation of new technology to improve operational efficiency | Improvement |  | Process implemented
Transparency | Adoption of iPads for use by Committees and boards, with folders for all meetings | Effectiveness
| Addition of meeting materials for all meetings on the county website | Improvement
| Development of a Listserv to automatically send agendas to the public and interested parties on a subscription basis | Improvement
| Addition of recordings from county board and committee meetings on the website | Improvement
GROWTH
STRATEGY | TACTIC / ACTION | STRATEGIC PRIORITY | RESPONSIBLE PARTY | PERFORMANCE METRIC | PERFORMANCE TARGET | START DATE | END DATE (if applicable) | ESTIMATED FINANCIAL COST | STATUS
Maintain investment in workforce and community development | Prioritize new home construction, and development using smart growth concepts. Smart growth planned economic and community development that attempts to curb urban sprawl and worsening environmental conditions | Growth |  | Year-over-year growth in new housing tied to county incentives/programs. | 2022 - incentives defined 2023 - 5-15 new homes developed as a result of county engagement
| Encourage improvements to existingproperty to increase attractiveness | Growth
| Support workforce development initiatives directed at attracting new residents | Growth
| Support and invest in broadband expansion throughout the county | Growth |  | Increase the number of county residents with high-speed internet | Annual growth in residents with Broadband Internet
| Identify financially sustainable use options for the UW Richland campus | Focus
| Continue to invest in community and economic development partnerships with a demonstrated return-on-investment | Focus |  | Request annual return on investment reports from funded partners, and monitor to ensure ROI is steady or grwoing across multiple year periods | Annual delivery of ROI reports by funded partners. Annual steady ROI or ROI growth.
Support business attraction and retention | Develop a portfolio of incentives to support business growth | Growth
| Identify priority areas in the county for future industrial, commercial, or residential development | Growth
| Identify future land uses for county or municipal-owned land informed by economic opportunities and environmental constraints | Growth
Improve county identity and marketing | Collaborate with county partners in the development of a distinctive brand for Richland County that will serve to build a sense of identity and pride, and help attract new residents and tourists | Growth |  | Create a distinct Richland County brand and marketing platform targeted at tourists and workforce | Branding completed by 2022
| Create a new website that improve the county’s digital presence, and serves both an effective governmental function as well as serving as an attractive “front door” to the world for new businesses, residents, and tourists looking to discover the county | Growth |  | Create a new website | Website creation by 2023
| Capitalize on the county’s natural beauty and recreational opportunities through the investment and marketing of county parks, campgrounds, and recreational opportunities | Growth |  | Develop or update the county's outdoore recreation plan to guide investment and enable recreation grants | Plan updated by 2022